## WA 2020-21 HIT Ops Plan
DRAFT -- HIT Operational Plan
Task ID | Category | Related requirement | CY 2022 Tasks
1 | EHRs
1-01 | Electronic Health Record As a Service (EHRAAS) |  | Q1 2022- Q2 2022 Develop provider communications plan Q1 2022 - Q4 2022 Begin implementation of provider communication plan Q1 2022-Finalize baseline implementation requirements The following tasks are contingent on funding: Q1 2022- Q4 2022 engage with lead Organization Q1 2022- ongoing Establish and engage Governance Group Q3 2022- Q4 2022 (and beyond) Begin provider onboarding Q2 2023- Q4 2023 (and beyond) Go-live with baseline implementation
1-02 | Administer EHR Incentive Project | 2019 project continuing | Q1 2022 - Q4 2022 Conduct audits of EPs/EHs and adjust for over/underpayments for EHs Q1 2022 - Q4 2022 Submit E-Reports to CMS. Q1 2022 - Q4 2022 Implement the plan to transition data for eMIPP attestation data into HCA warehouse.
2 | Crisis Call Center and Related Activities
2-01 | 988/SB1477 |  | Q1 2022 - Q3 2022 - Lead and engage in 988/1477 Staff Workgroup Q1 2022 review and comment on draft technical and operational plan submitted. Q3 2022 receive final technical and operational plan Q1 2022-Q3 2022 identify components, as required by legislation, needed for behavioral health integrated client referral system (including technical and user workflow) and connection to the Crisis call Center Hubs Q1 2022-Q4 2022 Participate upon request in subcommittees established by the Crisis Response Strategy Committee (CRIS)
3 | Mental Health IMD Waiver
3-01 | Financial map for BH HIT Plan | MH IMD Waiver State Medicaid programs should detail plans to support improved availability of non-hospital, non-residential mental health services including crisis stabilization and on-going community-based care. The financing plan should describe state efforts to increase access to community-based mental health providers for Medicaid beneficiaries throughout the state, including through changes to reimbursement and financing policies that address gaps in access to community-based providers identified in the state’s assessment of current availability of mental health services included in the state’s application. F.a Increase availability of non-hospital, non-residential crisis stabilization services, including services made available through crisis call centers, mobile crisis units, observation/assessment centers, with a coordinated community crisis response that involves collaboration with trained law enforcement and other first responders. F.b Increase availability of on-going community-based services, e.g., outpatient, community mental health centers, partial hospitalization/day treatment, assertive community treatment, and services in integrated care settings such as the Certified Community Behavioral Health Clinic model. | Q2 2022 - Q3 2022 Conduct financial mapping for MH IMD Waiver related activities (review any appropriated budget/funds for 2022; identify other funding sources as needed)
3-02 | Closed Loop Referrals and e-Referrals: | MH IMD Waiver 1.1 Closed loop referrals and e-referrals from physician/mental health provider to physician/mental health provider 1.2 Closed loop referrals and e-referrals from institution/hospital/clinic to physician/mental health provider 1.3 Closed loop referrals and e-referrals from physician/mental health provider to community based supports | Contingent on available funding: e-Referrals: Q1- Q4 2022 through CY 2024: - Design and Develop a standard Collective Medical (CM) Implementation Guide for ADTs and care plans for statewide use by psychiatric hospitals/units to inform community providers of discharge - Engage in awareness campaign regarding CM tools for Community-Based Psychiatric hospitals/units - Support implementation; training/TA/practice coaching for community-based psychiatric hospitals/units for the use of the CM ADT and care plan Closed-Loop Referral: Q3-4 2022 through CY 2026: - Pilot implementation of interoperable close-loop referral between community-based psychiatric hospitals/units and physicians (e.g., EPIC to Netsmart) and between physicians to mental health providers (e.g., Medallies to Netsmart)
3-03 | Create and use Electronic Care Plans that are interoperable | MH IMD Waiver 2.1 The state and its providers can create and use an electronic care plan 2.2 E-plans of care are interoperable and accessible by all relevant members of the care team, including mental health providers | Contingent on Funding: See Task 3-02 related to "Closed Loop Referrals and e-Referrals"
3-04 | Medical Records Transition. | MH IMD Waiver 2.3 Medical records transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.4 Electronic care plans transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.5 Transitions of care and other community supports are accessed and supported through electronic communications MMC IMC contract language: 14.1.9 Continuity and Care Coordination for Transition Age Youth (TAY): 14.1.9.1 The Contractor shall develop a comprehensive transition plan in collaboration with other systems and providers, including agencies contracted to provide services to Youth, that identifies the Enrollee’s goals, objectives, and strategies to achieve goals. The transition plan shall take into account the following: 14.1.9.1.1 Individual behavioral and physical health needs, which may include continued services in the adult behavioral or physical health systems. The transition plan shall address the need for continuity and coordination of services and supports for the Enrollee and the Enrollee’s family and identify developmentally and culturally appropriate adult services; 14.1.9.1.2 Connections with supportive housing and supported employment services through the Foundational Community Supports program, post-secondary education, technical training, housing community support, natural supports, and cross-system coordination as needed to attain the Enrollee’s goals. 14.13.14 Prioritizing WISe For Youth Discharging From CLIP: The Contractor must prioritize access to WISe services for all youth qualified to receive WISe services that are discharging from CLIP. 14.13.15 Rehabilitation Case Management (RCM): The Contractor must provide Rehabilitation Case Management (RCM) throughout the entirety of the CLIP treatment from preadmission through discharge. RCM includes a range of activities conducted in or with a facility for the direct benefit of the admitted youth to improve treatment gains and plan for successful discharges from CLIP. Activities include: 14.17.3.1 The Contractor must complete the Uniform Discharge Tool reporting template for every individual discharging from a mental health inpatient setting hospital stay. The template, developed collaboratively with contracted MCOs and HCA, will be finalized by the end of the first quarter of 2019 and submitted afterward as described below: ... 14.17.3.5 The Contractor, in collaboration with all hospitals including state hospitals; and other facilities that provide care for individuals with 90 and 180-day civil commitments, shall develop discharge planning policies and procedures. 14.17.3.5.4 The Contractor must accept the ’honor authorization’ for SUD residential admission when services are authorized by the Enrollee’s previous MCO, in cases where an incarcerated Enrollee is authorized by one MCO but changes to another MCO upon release. 14.17.4 Care coordination and transitions between levels of care – Inpatient Treatment Agencies. 14.17.4.1 The Contractor must require that behavioral health treatment agencies develop policies and procedures that enhance care coordination, including transitions between all levels of care, by July 1, 2019. Any new policies or procedures must take effect on or before October 1, 2019. 14.17.4.2 The Contractor must work with behavioral health treatment agencies to ensure there is adequate coordination for Enrollees transitioning between various levels of treatment services to ensure continuity of care. As used in this section, “continuity of care” means the situation under which an Enrollee who is receiving services from an individual provider is entitled to receive timely and applicable follow-up services from ancillary referral agencies with the goal of providing immediate follow-up to address the holistic needs of the Enrollee. This will include, at a minimum, the following: 14.17.4.3 The Contractor must work with the Subcontractor to ensure that discharge plans and facilitation to post-discharge services are documented in the Enrollee’s electronic health record. The following must occur when the Enrollee is discharged or transitioned to a lower or higher level of care: 14.17.4.3.1 Appropriate referrals are made to a behavioral health provider and coordination with the Enrollee’s MCO. 14.17.4.3.2 Follow up appointments must be scheduled to occur within seven calendar days of Enrollee discharge and documented as such in the Enrollee’s electronic health record. Documentation must include: 14.17.4.3.2.1 Release of Information between behavioral health treatment agencies for the Enrollee; date and time of appointment; any current medications; and 14.17.4.3.2.2 If applicable, sufficient supply and compliance plan for prescribed medications is documented as part of the discharge process. 14.17.4.3.3 Enrollee’s counselor or a designated outreach coordinator at the facility, will follow up via telephone, text message, or email with the Enrollee within one week post-discharge. 14.17.5 Transition from Inpatient SUD Behavioral Health Agency. The Contractor must coordinate with Subcontractors who provide inpatient treatment to ensure referrals of Enrollees to outpatient services post-discharge from their facility. This includes the following:... 14.17.5.2.1.4 Housing. Enrollee’s housing status must be verified through the Enrollee or authorized representative and documented within the electronic health record system. When necessary, the Behavioral Health facility will refer Enrollee to housing and community support services; documentation of any referrals must be placed in the electronic health record. When the Enrollee is prescribed FDA approved medications for SUD, the provider must document efforts to obtain housing to fit the individual’s needs. 14.17.5.2.1.5 Transportation- Arrange for transportation for the individual, as needed, to scheduled appointments and recovery-based housing. | Contingent on available funding: Q3-4 2022 through CY 2026: Support and pilot the creation and exchange of electronic summary of care documents (e.g., CCDs/other health records) as individuals transition across systems of care, including from youth oriented systems of care to and from adult systems of care.
3-05 | Consent - E-Consent (sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws)) | MH IMD Waiver 3.1 Individual consent is electronically captured and accessible to patients and all members of the care team, as applicable, to ensure seamless sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws) | Contingent on available funding: - HCA will procure vendor to design, develop, and implement an electronic consent management (e-CM) solution. The e-CM solution will support information exchange on behalf of persons with substance use disorder and co-occurring mental health conditions.
3-06 | Interoperable Intake, Assessment, and Screening tools: data is interoperable with the rest of the HIT ecosystem | MH IMD Waiver 4.1 Intake, assessment and screening tools are part of a structured data capture process so that this information is interoperable with the rest of the HIT ecosystem. | Contingent on available funding, Q3 and Q4 2022 through CY 2026, in consultation with Subject Matter Experts, HCA will: 1. Identify one of each of the following tools in use in WA State: intake, assessment, and screening tools 2. Coordinate w/ ONC and CMS (and other states) to determine the availability/applicability of HIT standards (content and exchange) for the selected intake, assessment and screening tools. 3. When tools have not been linked HIT standards, request standards from Standards Development organizations (SDOs) 4. Create FHIR enabled interoperable exchange tools for each selected intake, assessment, and screening tool 5. Identify 3-6 mental health providers to pilot the creation and exchange with their trading partners of interoperable intake, assessment, and screening tools
3-07 | Telehealth | MH IMD Waiver 5.1 Telehealth technologies support collaborative care by facilitating broader availability of integrated mental health care and primary care Rural Health EHR | Q1 2022 - Q4 2022: Incorporate, as appropriate, into existing HCA activities that involve the use of telehealth (e.g. EHRAAS, DBHR contracts with UW and/or BHI) development of guidance on/use of telehealth platforms that appropriately protect patient privacy and security. Q4 2021- Q1 2022 - Q4 2022: Coordinate and collaborate Department of Commerce/WA State Office of Broadband to identify and begin to address gaps, in the broadband infrastructure to support virtual health and social service delivery in the State.
3-08 | Analytics: the state can identify patients at risk for discontinuing/ stopping treatment and alerting care teams | MH IMD Waiver 6.1 The state can identify patients that are at risk for discontinuing engagement in their treatment, or have stopped engagement in their treatment, and can notify their care teams in order to ensure treatment continues or resumes (Note: research shows that 50% of patients stop engaging after 6 months of treatment ) MMCO IMC Contract language: 14.17.5.3 If the Enrollee discontinues services, the Subcontractor will document as such and attempt to facilitate transition back into the community. | Contingent on available funding, CY 2023 and CY 2024: HCA will engage a contractor to: 1. Identify characteristics of individuals that stop their engagement in their treatment; and 2. Using these characteristics, develop a model that predicts when individuals are at risk for stopping treatment.
3-09 | Health IT is being used to advance the care coordination workflow | MH IMD Waiver 6.2 Health IT is being used to advance the care coordination workflow for patients experiencing their first episode of psychosis | Contingent on available funding, Q3 and Q4 2022 through CY 2023: HCA will support the following activities: 1. Develop a standard Integrated Clinical Assessment template for Washington State (aka the WA-ICA) that includes quantitative and qualitative responses. 2. Develop a web-based portal into which providers' WA-ICA results can be submitted and from which benchmarking reports can be generated and transmitted; 3. Develop quantitative reporting algorithms and standard report templates (that incorporate quantitative and qualitative results); 4. If needed, secure security design review of the templates and portal; 5. Test and refine template and web-based portal; and 6. Draft recommendations to support ongoing implementation, maintenance, and use of the WA-ICA.
3-09 | Electronic medical records capture all episodes of care, and are linked to the correct patient | MH IMD Waiver 7.1 As appropriate and needed, the care team has the ability to tag or link a child’s electronic medical records with their respective parent/caretaker medical records | HCA will propose adding use cases to the Coalition MPI Roadmap that would support using the Coalition MPI to enable linking electronic medical records across all episodes of care
4 | APMs
4-01 | HCA Payment Innovation |  | Support HCA payment innovation activities to integrate, as appropriate, use of HIT/HIE tools/resources, including: Q1 2022 - Q3 2022: Medicaid Multi-Payer Primary Care Payment Initiative -- referred to as the Primary Care Transformation Model (PCTM): (i) Consider whether and if so, how to incorporate the use of HIT/HIE in the provider certification model being developed for the PCTM (ii) Consider whether and if so how, the "transformation fee" to implemented as part of the PCTM will be used to incent/support the adoption and use of HIT (e.g., HIE and /or CIE to support care coordination) Q1 2022 - Q2 2022: Community Health Access and Rural Transformation (CHART) Model (i) Consider whether and if so, how the use of HIT/HIE will support the CHART Model, including use by rural hospitals in care re-design; and if applicable, incorporate the use of HIT/HIE in the CHART Rural Health System Transformation Plan.
5 | Digital Quality Measures
5-01 | Advancing Digital Quality Measures |  | Explore options to advance the use of digital Quality Measures (dQMs) in MCOs contracts, APMs, and other HCA initiatives, including: - focusing on priority dQMs that may include, but not limited to, the two dQMs for which HCA has presently acquired specifications; and - considering the roles and responsibilities, as appropriate, of HCA, MCOs, OHP, providers, and others.
6 | SDOH and LTC/Social Service Data Exchange
6-01 | Electronic creation, exchange, and re-use of SDOH data |  | Q1-Q3 2022 Develop a white paper on opportunities in WA State to support the electronic creation, exchange, and re-use of Social Determinants of Health (SDOH) data for administrative and caregiving purposes. The paper will be written in collaboration with/input from staff from State agencies (e.g., HCA, DSHS), MCOs, providers, and others. The paper will be framed around the creation, exchange and re-use of SDOH data that could be captured in a modernized Integrated Eligibility and Enrollment (IE&E) system.
6-02 | Strategy to Advance HIT/HIE in Social Service Programs |  | Q1 - Q4 Contingent on the availability of resources, DSHS, in collaboration with and support from HCA, will develop a Strategy and Operational Plan to advance the use of HIT/HIE to support transitions in LTC. The Strategy and Operational Plan will identify (i) goals, key priorities, and programmatic and implementation opportunities to advance the use of HIT/HIE and (ii) options to advance the use of interoperable technology to support information exchange for transitions in LTC. The Strategy and Operational Plan will be informed by input from State agency staff, payers and plans, Accountable Communities of Health (ACHs), Area Agencies on Aging (AAAs), and service providers.
6-03 | Collective Medical and LTC Transitions in Care |  | Q1 - Q4: In collaboration with DSHS and upon invitation from the HH ACH, HCA will participate in the HHACH initiative to advance the use of Collective Medical (CM) tools to support transition in care involving LTC.
6-04 | WA State Gravity Project |  | Q1-Q4 2022 Continue participation and collaboration in WA State Gravity project to develop a pilot on the interoperable exchange of SDOH data, including (if possible) referrals for non-emergency medical transportation to access needed health-related social services (e.g., food).
7 | CMS Interoperability Rules
7-01 | Patient Access API |  | Q1 - Q2 2022-identify lessons learned and update as necessary
7-02 | Provider Directory API |  | Q1 - Q2 2022-identify lessons learned and update as necessary
4 | Master Person Index
7-03 | HHS Coalition MPI Project |  | Q2 2022-MPI architecture completed development Q3 2022-MPI go-live with initial system connections
8 | CDR Functions
8-01 | Clinical Data Repository |  | Q1 2022- Ongoing: Jails to query CDR for clinical information
8-02 | Transmit Tribal FFS data to CDR. |  | CY 2023: Contingent on availability of an e-CM tool and development of HCA Data Governance guidance, HCA will produce daily tribal FFS extracts and transmit to CDR
9 | MTP, Extension, and Waiver Renewal
9-01 | MTP Activities |  | Q1 - Q4 2022: Support MTP Program on: - HIT/HIE/CIE activities in Waiver Extension, and - Support MTP program planning for Waiver Renewal and inclusion of HIT/HIE/CIE activities
10 | Tribal Engagement
10-01 | Have conversations with Tribes about Exchanging Health Information | 2019 project continuing | Q1 - Q4 2022: HCA will continue conversations with Tribal partners and the AIHC on the value of HIE, the need to limit/protect access to tribal members health information, how the technical solution to be deployed for consent management could be extended to protect tribal members health information in the CDR, and solicit Tribal/AIHC input on HIE use cases.
10-02 | Assist Tribes exploring EHR replacement and system integration | 2019 project continuing | Ongoing: Upon request by AIHC and/or tribal partners, HCA will provide technical assistance to Tribes exploring EHR replacement and system integration, including use of the statewide EHRAAS and its implementation for BH providers .
10-03 | Support Tribal Adoption of CDR | 2019 project continuing | Q2 2022: HCA will continue to include Tribes and data sovereignty as a key use case in any e-consent management solution discussions
10-04 | Discuss TARGET replacement with Tribal providers |  | Q2 2022 and beyond: If a TARGET System replacement is needed before a statewide EHRAAS is implemented, HCA HIT Section will work with Tribal Partners to: - Identify gaps created by moving away from TARGET system - Identify requirements to ensure system replacement doesn't break existing processes by Tribal providers