## Sheet1
Final -- 2023 HIT Operational Plan
Task ID | Category | Related requirements/information | CY 2023 Tasks
1 | EHRs
1-01 | State Electronic Health Record |  | Q1 - Q2 2023: HCA, in collaboration with the OCIO/WaTech (the lead agency for this work) and other state agency partners (i.e., DOC, DSHS), will develop, by 6/30/2023, a plan for procuring and implementing a state electronic health record (EHR) solution. The plan must include additional funding sources, such as CMS funding. Q1 - Q2 2023: HCA and agency partners will work with DES to develop by 6/30/2023 the procurement strategy for the state EHR.
2 | Crisis Call Center and Related Activities
2-01 | 988/HB E2SHB 1477 |  | Q1-Q4 2023: Identify needed technology components, as required by legislation. Q1-Q4 2023: Monitor Vibrant Emotional Health activities related to the Vibrant Unified Platform Q1-Q2 2023: Identify and select document types to be standardized and made interoperable (e.g., Next Day Appointments, MH Advanced Directives, Safety Plans, level of care assessments, etc.). Q2-Q4: Contingent on funds: support work to make selected documents standard and interoperable; engage in work related to bed registries and referrals (including closed loop referrals), including as needed identify user workflows; support provider and patient use of resource directories (e.g., provider and social service directories) Q1-Q3 2023: Conduct analysis of use of the 911 technical infrastructure and the PROs/CONs of using parts of the technical infrastructure for crisis calls and response, including: collaboration with the WA State Military Department; review of related legislation/implementation in CA; exploration of the Next Gen 911 NENAi3 standards and utility for 988; and identify activities that could be implemented to support the use of this technical infrastructure in Washington State. Q1-Q4 2023: Participate in CRIS committee meetings as needed. Q1-Q4 2023: Participate in HMA 1477 activities (e.g. committee progress reports, funding recommendations for the 988 line tax). Q1-Q4 2023: Participate and collaborate with the Governor's office, DBHR, and DOH regarding 1477 tasks. Q2-Q3 2023: Publish and evaluate responses to the RFI. Q3-Q4 2023: Contingent on funds: develop and publish RFP.
3 | Electronic Consent
3-01 | Description: Electronic Consent consistent with applicable law and regulations. |  | Contingent on funding: Q1 2023: Procure vendor supporting SUD consents. Q1 2023: Announce Apparently Successful Bidder (ASB) and negotiate contract. Q2 2023: Secure CMS approval of Electronic Consent management (ECM) solution. Q2 2023: Finalize implementation plan with the solution vendor. Q2-Q3 2023: Vendor design, build, and test solution; and request vendor to consider extensibility of ECM in view potential of Federal Government changes to 42 CFR Part 2. Q2-Q4 2023: Continue to execute stakeholder, partner outreach, and communications plan. Focus on the behavioral health community for early system users. Q3-Q4 2023: Develop training material for internal and external users. Q4 2023: Train early system users (internal and external). Q3-Q4 2023: Operational Readiness Review (ORR) for CMS certification of consent module. Q4 2023: Deploy the baseline solution.
4 | Mental Health IMD Waiver | CMS MH IMD Waiver Implementation Plan: State Medicaid programs should detail plans to support improved availability of non-hospital, non-residential mental health services including crisis stabilization and on-going community-based care. The financing plan should describe state efforts to increase access to community-based mental health providers for Medicaid beneficiaries throughout the state, including through changes to reimbursement and financing policies that address gaps in access to community-based providers identified in the state’s assessment of current availability of mental health services included in the state’s application. F.a Increase availability of non-hospital, non-residential crisis stabilization services, including services made available through crisis call centers, mobile crisis units, observation/assessment centers, with a coordinated community crisis response that involves collaboration with trained law enforcement and other first responders. F.b Increase availability of on-going community-based services, e.g., outpatient, community mental health centers, partial hospitalization/day treatment, assertive community treatment, and services in integrated care settings such as the Certified Community Behavioral Health Clinic model.
4-01 | Description: Project and Financial Planning for HIT Implementation |  | Q1-Q2: Identify and engage a contractor to develop a strategic plan for spending future MH IMD Waiver HIT dollars as well as other funds that support efforts to advance the use of HIT/HIE in the community based mental health system, including crisis services, as required in the MH IMD Waiver. Q1- Q4 2023: Identify funding sources that could be used to support HIT Tasks in the MH IMD Waiver Q2-Q3 2023: Participate in budget discussions and develop needed documents to advance requests for funds to support MH IMD Waiver HIT tasks (e.g., develop Concept Papers, Decision Packages)
4-02 | Description: Closed Loop Referrals and e-Referrals | CMS MH IMD Waiver Requirement 1.1 Closed loop referrals and e-referrals from physician/mental health provider to physician/mental health provider 1.2 Closed loop referrals and e-referrals from institution/hospital/clinic to physician/mental health provider 1.3 Closed loop referrals and e-referrals from physician/mental health provider to community based supports | Q1 -Q2 2023: Using the contractor engaged for Task 4-01: Identify and plan for the implementation of referral tools that: support referrals between physicians, mental health providers, institutions/hospitals/clinics, and community-based supports; and interoperate with the crisis system. Q3 -Q4 2023: Contingent on Funds: Begin implementation of tasks to support electronic referrals.
4-03 | Description: Create and use Interopeable Electronic Care Plans | CMS MH IMD Waiver Requirement 2.1 The state and its providers can create and use an electronic care plan 2.2 E-plans of care are interoperable and accessible by all relevant members of the care team, including mental health providers | Q1 -Q2 2023: Using the contractor engaged for Task 4-01: Identify and plan for the implementation of interoperable, electronic care plans that would be accessible by all relevant members of the care team, including mental health providers. Q3 -Q4 2023: Contingent on funds: Begin implementation of tasks for the creation and use of interoperable, electronic care plans.
4-04 | Description: Medical Records Transition | MH IMD Waiver Requirement 2.3 Medical records transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.4 Electronic care plans transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.5 Transitions of care and other community supports are accessed and supported through electronic communications | Q1 -Q2 2023: Using the contractor engaged for Task 4-01: Identify and plan for the implementation of the electronic creation and exchange of key medical record documents including care plans and patient generated documents (e.g., mental health advance directives) to support transitions in care including transitions from youth-oriented systems of care to the adult behavioral health system. Q3 -Q4 2023: Contingent on funds: Begin implementation of tasks related to the creation and exchange of interoperable, electronic documents to support transitions in care.
4-05 | Description: Electronic Consent consistent with applicable law and regulations. | MH IMD Waiver Requirement 3.1 Individual consent is electronically captured and accessible to patients and all members of the care team, as applicable, to ensure seamless sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws) | See Task 3-01
4-06 | Description: Interoperable Intake, Assessment, and Screening tools | MH IMD Waiver Requirement 4.1 Intake, assessment and screening tools are part of a structured data capture process so that this information is interoperable with the rest of the HIT ecosystem. | Q1 -Q2 2023: Using the contractor engaged for Task 4-01: Identify and plan for the implementation of interoperable intake, assessment and screening tools, including tools needed across the BH continuum (e.g., tools needed by mental health and crisis providers, state psychiatric hospitals). Contingent on funds: Q3 -Q4 2023: Begin implementation of a process to standardize and make interoperable needed intake, assessment and screening tools. The process would include: - selecting the intake, assessment and screening tool(s) to be interoperably exchanged using FHIR APIs - creating FHIR-enabled interoperable exchange tools for selected intake, assessment, and screening tool - developing a plan to pilot the exchange and use of electronic, interoperable intake, assessment and screening tools including by mental health and crisis providers - if feasible, piloting the exchange and use of electronic, interoperable intake, assessment and screening tool(s)
4-07 | Description: Telehealth | MH IMD Waiver Requirement 5.1 Telehealth technologies support collaborative care by facilitating broader availability of integrated mental health care and primary care | Q1 -Q2: Support Behavioral Health Institute (BHI) Tele-Behavioral Health Summit on May 9th and 10th. The Summit will provide: (i) education on acquisition and use of needed tele-behavioral tools for community-based providers (e.g., mental health (MH) and primary care providers) that serve persons with MH needs; and (ii) training on professional tele-behavioral encounters.
4-08 | Description: Identifying patients at risk for discontinuing/ stopping treatment | MH IMD Waiver Requirement 6.1 The state can identify patients that are at risk for discontinuing engagement in their treatment, or have stopped engagement in their treatment, and can notify their care teams in order to ensure treatment continues or resumes (Note: research shows that 50% of patients stop engaging after 6 months of treatment ) | Contingent on available funding: Q3 and Q4: Engage a contractor to identify: (i) whether/how PRISM is used, including by MCOs, to identify patients at risk and any gaps that need to be addressed; (ii) how care teams are notified of patients at risk to ensure continuation of service, and (iii) whether/how technology is / could be used to support these activities.
4-09 | Description: Health IT used to advance care coordination workflow for First Episode Psychosis | MH IMD Waiver 6.2 Health IT is being used to advance the care coordination workflow for patients experiencing their first episode of psychosis | Q1 - Q2 2023: Using funds appropriated for the MH IMD Waiver HIT activities and Mental Health Block Grant (MHBG) for individuals experiencing their first episode of psychosis, contract for the following activities: o development of a Strategic Vision and Operational Plan for the Enhanced Central Assessment of Psychosis Service (CAPS) supporting the New Journeys program, including resources needed/used to: - identify and screen for psychosis in youth and young adults; - standardize screening tools and assessments to identify individuals experiencing their first episode of psychosis; and - increase awareness and use of the New Journeys program. o Identify Options for the Central Registry for CAPS, including: - Identify and evaluate options for developing and implementing a central registry into which needed assessments could be submitted and accessed. - Identify content to be included in the registry; - Develop governance rules regarding who would be able to submit and access assessments in the Central Registry for CAPs
4-10 | Description: Electronic medical records capture all episodes of care, and are linked to the correct patient | MH IMD Waiver 7.1 As appropriate and needed, the care team has the ability to tag or link a child’s electronic medical records with their respective parent/caretaker medical records | This Waiver requirement will first require use of a Master Person Index (MPI). Work is underway to implement MPI. Once the MPI is widely implemented, work to link parent/child records could be planned.