## Complete HIT OP 2017 - 2018
The Health IT Operational Plan 2017 to 2018 identifies the tasks and timelines needed to execute the Health IT Strategic Roadmap and will be updated annually. The Health IT Strategic Roadmap is located at: https://www.hca.wa.gov/assets/program/health-information-technology-strategic-roadmap.pdf | [14 empty] | Internal (HCA Participants) | [16 empty] | External (Other Participants)
Activity | Sub-Activity | Task Number | Task | Design | Implementation Operations | Evaluation | Activity Type | Q4-17 | Q1-18 | Q2-18 | Q3-18 | Q4-18 | Lead Responsible Party | Co Lead | AIM | Contracts | CQCT | Data Governance Program | EDMA | ERB | ETS | Financial Services | HCA ELT | HCA / Legal | HIT Section | HW / Communications | HW-Policy | MITA | MPOI | P1OS | Privacy Office | ACH / Providers | ACHs | APCD | DOH | DoC / Jails | DSHS | DSHS / RDA | FHCQ | Indian Health Care Providers | KCACH | MCOs | OHP | ProvCore | SAMHSA | Tribal Governments | WHA | Provider Association
Monthly Meeting | Monthly Meeting | 01-001 | Public/private monthly meeting supported by HCA to discuss and report out on topics related to the execution of activities in the HIT Operational Plan (e.g., activities undertaken in the previous month, activities to be undertaken in the upcoming month, issues encountered). | X | X | X | Governance | [5 empty] | HIT Section | ACH | Participant |  | Participant | Participant | Participant |  |  | Participant |  |  | Lead |  | Participant |  |  | Participant | Participant | Participant | Co-Lead |  |  | Participant | Participant |  |  |  |  | Participant | Participant |  |  | Participant |  | Participant
Monthly Meeting | Monthly Meeting | 01-002 | Monthly meeting participation: - Membership determined by participating organizations (and may vary based on depending on Activity and specific tasks) - Members are expected to complete “homework” (i.e., assigned Tasks in each Activity) in between monthly meetings - Participants may wish to consider using “centers of expertise” to address activities and tasks | X | X | X | Governance
Data | Data | 02-001 | HCA will work with ACHs to create a list of high value data sources needed for project implementation planning and project implementation by project area. HCA will identify those data needs that the State can address (including those data needs/sources of DOH, DSHS, DOC, other state agencies), and will work with ACHs to collaborate on identifying additional data sources. In creating the list of data sources, HCA will use and extend the Data Inventory created by Manatt. HCA will present a proposal on how this list could be maintained. | X | X | X | Governance | [5 empty] | AIM | EDMA | Lead |  | Participant | Participant | Co-Lead | [5 empty] | Participant |  | Participant |  |  | Participant |  | Participant | Participant |  | Participant | Participant | [5 empty] | Participant | Participant |  |  |  |  | Participant
Data | Data | 02-002 | HCA, in collaboration with Other Participants, will take into account whether the following data needs/sources are needed to address provider/ACH near and long-term data needs and included in the Inventory: • Social Determinants of Health (SDOH) Data (e.g., transportation; food, housing, school, employment security; childcare): A possible source: WIN 2-1-1 (SDOH Data) • ICD10 z-codes •Paramedicine/EMS • Behavioral Health/Functional Status Assessment Data • Claims Data • MCO encounter data • Linkages between financial/clinical data • Prism • APCD • CDR | X | X | X | Policy | [5 empty] | AIM | EDMA | Lead |  | Participant | Participant | Co-Lead | [5 empty] | Participant |  | Participant |  |  | Participant |  | Participant | Participant |  | Participant | Participant | [5 empty] | Participant | Participant |  |  |  |  | Participant
Data | Data | 02-003 | HCA, in consultation with Other Participants will use the longer-term gap analysis to propose recommended policies, governance and infrastructure changes (including recommendations for leveraging clinical and claims data to support quality measurement/analytic activities) | X | X | X | Policy | [5 empty] | AIM | HW/Policy Data Governance HIT Section | Lead |  | Participant | Co-Lead | [6 empty] | Co-Lead |  | Co-Lead |  |  | Participant |  |  | Participant |  | Participant | Participant |  | Participant |  |  |  | Participant
Data | Cross-state / best-practices review | 02-004 | HCA will share information learned via the cross-state / best-practices review (performed under contract with Manatt) including information on: the data that is exchanged/methods of exchange by Social Service providers (e.g., housing, transportation, jails, employment) with physical health providers. | X | X | X | Policy | [5 empty] | HW/Policy | EDMA | Participant |  |  | Participant | Co-Lead | [5 empty] | Participant |  | Lead |  |  | Participant | Participant |  | Participant |  |  | Participant | [5 empty] | Participant
Data | HCBS Providers and HIPAA | 02-005 | HCA will review existing P1 project artifacts related to whether HCBS providers are HIPAA covered entities. HCA will determine whether additional analysis needed and if so, in what area(s). HCA will disseminate to other participants information related to whether social service providers are HIPAA covered entities. | X | X |  | Governance | [5 empty] | P1OS | Privacy Office | Participant |  |  | Participant | [6 empty] | Participant |  |  |  |  | Lead | Co-Lead | Participant |  |  |  |  | Participant |  |  |  |  | Participant |  |  | Participant |  |  | Participants
Data | SAMSHA Reporting Requirements | 02-006 | HCA, in collaboration with Other Participants will (i) identify and streamline as much as possible behavioral health reporting requirements (e.g., SAMHSA reporting requirements) and (ii) consider whether reporting requirements align with HIE standards | X | X |  | Governance | [5 empty] | EDMA | HW/Policy P1OS | Participant |  |  |  | Lead | [5 empty] | Participant |  | Co-Lead |  | participant | Co-Lead |  | Participant |  |  |  |  | Participant |  |  |  |  | Participant |  |  | Participant |  |  | Participants
Data | SAMSHA Reporting Requirements | 02-007 | HCA will disseminate information on the results of streamlining and aligning behavioral health reporting requirements to Other Participants | X | X |  | Governance | [5 empty] | EDMA | HW/Policy P1OS | Participant |  |  |  | Lead | [5 empty] | Participant |  | Co-Lead |  | participant | Co-Lead |  | Participant |  |  |  |  | Participant |  |  |  |  | Participant | [5 empty] | Participants
Data | Patient to Provider Attribution | 02-008 | Patient to Provider Attribution: HCA will: 1. consult with Other Participants to determine need for/methods/ approaches/ gaps in patient/provider attribution 2. synthesize and disseminate information 3. determine and communicate the approach(es) HCA will use for patient/provider attribution | X | X |  | Policy | [5 empty] | AIM | EDMA HIT Section | Lead |  |  | Participant | Co-lead | [5 empty] | Co-Lead |  | Participant |  |  |  |  | Participant | Participant | [8 empty] | Participant | [5 empty] | Participants
Data Governance Strategy | Data Aggregation | 03-001 | HCA will take into account: (i) activities related to the Data Inventory and (ii) the Manatt data gap analysis and consult with external stakeholders (when appropriate) to gather information regarding data aggregation needs. HCA will: - define data aggregation and options/legal framework to allow for needed information exchange and utilization by ACHs; and - identify, describe and present to HCA leadership data aggregation options (including those below), identify PROs and CONS of options (including sustainability of options post-MTD) HCA leadership will determine which data aggregation option(s) HCA will support. HCA will disseminate white paper describing options considered, option(s) selected, and rationale Claims data aggregation options include: • APCD • Providence Core • Clinigence • OHP • State agencies (including HCA) • Other contracted data aggregator |  | X |  | Governance | [5 empty] | Data Governance | Privacy Office AIM | Co-Lead |  |  | Lead | [6 empty] | Participant |  | Participant |  |  |  | Co-lead |  | Participant
Data Governance Strategy | Data Aggregation | 03-002 | APCD – build (2017) and buy products (2017-2018) |  | X |  | Infrastructure | [5 empty] | AIM | EDMA | Lead |  |  |  | Co-Lead | [5 empty] | Participant
Data Governance Strategy | Data Aggregation | 03-003 | HCA will invest in data aggregation vendor support (i.e., Clinigence) for payment model 4. |  | X | X | Infrastructure | [5 empty] | AIM |  | Lead | [9 empty] | Participant |  | Participant
Data Governance Strategy | Data Aggregation | 03-004 | Master Data Management – Phase 2 | X | X |  | Infrastructure | [5 empty] | EDMA | AIM | Co-Lead |  |  |  | Lead | [5 empty] | Participant
Data Governance Strategy | Data Aggregation | 03-005 | Truven/IBM Data Model – Phase 2 | X | X |  | Infrastructure | [5 empty] | EDMA | AIM | Co-Lead |  |  |  | Lead | [5 empty] | Participant
Data Governance Strategy | Data Aggregation | 03-006 | Model 2 analytic support from the AIM team/DSHS-RDA | X | X | X | Analytics | [5 empty] | AIM | DSHS/RDA | Lead | [22 empty] | co-lead
Data Governance Strategy | Data Aggregation | 03-007 | Potential Provider One updates, tool built for FQHC/RHC APM 4 Payment Model 2 | X |  |  | Infrastructure | [5 empty] | P10S | AIM | Co-Lead | [14 empty] | Lead
Data Governance Strategy | Data Governance Guidelines | 03-008 | HCA, in consultation with Other Participants, will develop and disseminate Data Governance Guidelines on 2-3 areas identified as high priority use cases. Use cases could include such as topics as sensitive populations, small numbers reporting, data categorization, data sharing, consent management, access management, etc. HCA could also consider the need to align guidelines across agencies/programs (including DOH small numbers guidelines). |  | X |  | Governance | [5 empty] | Data Governance | Privacy Office | Participant |  |  | Lead | [6 empty] | Participant |  | Participant |  |  |  | Co-lead | Participant | Participant |  | Participant | Participant | Participant |  |  |  |  | Participant | Participant |  |  |  |  | Participants
Data Governance Strategy | Data Governance Guidelines | 03-009 | ACHs will: • ID targeted use cases; and • apply HCA guidelines to use cases |  | X |  | Governance | [5 empty] | ACH's | ACHs | Participant |  |  | Participant | [6 empty] | Participant |  | Participant | [5 empty] | Lead |  | Participant | Participant | Participant |  |  |  |  | Participant
Data Governance Strategy | Privacy and Exchange of SUD and other sensitive information | 03-010 | HCA and DSHS will consult with SAMHSA in order for the State to specify/clarify operational parameters of 42 CFR Part 2 and share information with ACHs, Providers, and Others |  | X |  | Policy | [5 empty] | Privacy Office | Data Governance HIT Section DSHS | Participant |  |  | Co-Lead | [6 empty] | Co-Lead |  | Participant |  |  |  | Lead | Participant | Participant |  |  |  | Co-Lead | [5 empty] | Participant |  |  |  |  | Participants
Data Governance Strategy | Privacy and Exchange of SUD and other sensitive information | 03-011 | HCA will collaborate with ONC in establishing an ONC-convened state learning collaborative (e.g., webinars) through which States could share practices, raise questions/concerns, and seek guidance on the exchange, re-use, and consent management of sensitive/SUD information. | X | X |  | Policy | [5 empty] | HIT Section | Privacy Office | Participant |  |  | Participant | [6 empty] | Lead | [5 empty] | Co-lead | [5 empty] | Participant
Data Governance Strategy | Privacy and Exchange of SUD and other sensitive information | 03-012 | HCA will participate in the ONC convened state learning collaborative on sharing/re-using sensitive/SUD information and will encourage other WA State agencies (e.g., DSHS) to participate. | X | X |  | Policy | [5 empty] | HIT Section | Privacy Office | Participant |  |  | Participant | [6 empty] | Lead | [5 empty] | Co-Lead |  |  |  |  | Participant | Participant
Data Governance Strategy | Privacy and Exchange of SUD and other sensitive information | 03-013 | HCA, in collaboration with other WA State agencies, will share with ACHs, providers, OHP, others information learned regarding the exchange, re-use, and consent management of sensitive/SUD information. | X | X |  | Policy | [5 empty] | HIT Section | Privacy Office | Participant |  | Participant | Participant | [6 empty] | Lead |  | Participant |  |  |  | Co-Lead | Participant | Participant | [9 empty] | Participant |  |  |  |  | Participants
Data Governance Strategy | Privacy and Exchange of SUD and other sensitive information | 03-014 | HCA, in collaboration with ACHs and providers, will: (i) identify the components/considerations/methods to pilot the exchange, re-use, and consent management of SUD information in compliance with 42 CFR Part 2, and (ii) develop a strategy to implement those components. In identifying methods to pilot consent management solutions, consideration will be given to piloting in integrated delivery systems. | X | X |  | Policy | [5 empty] | HIT Section | AIM | Participant |  |  | Participant | [6 empty] | Lead | [5 empty] | Participant |  | Participant |  |  | Participant | Participant | [5 empty] | Participant |  |  |  |  | Participants
Data Governance Strategy | Data Sharing Agreements | 03-015 | Work on Data Sharing Agreements (DSAs) will be informed by: Data Aggregation, Data Governance, Privacy/ exchange of claims/clinical information. Activities include collaborative work to develop a DSA for : a. research/ QM activities. b. information exchange at the point of care (including exchange of SUD/sensitive information (e.g., Consent Management template)) |  | X |  | Governance | [5 empty] | Data Governance | Contracts ACHs | Participant | Co-lead |  | Lead | Participant | [5 empty] | Participant |  | Participant |  |  |  | Participant |  | Co-Lead
Data Governance Strategy | Data Sharing Agreements | 03-016 | HCA will consult with the ONC to better understand the requirements and timelines in the 21st Century Cures Act that pertain to a Common Agreement at the nationwide level. |  | X |  | Policy | [5 empty] | HIT Section | Legal Office | Participant |  |  | Participant | [5 empty] | Co-Lead | Lead |  | Participant |  |  |  | Participant
Data Governance Strategy | Data Sharing Agreements | 03-017 | Taking into account information (i) learned from Tasks related to Data Aggregation, Data Governance, and Privacy/ exchange of information and (ii) regarding requirements in the 21st Century Cures Act regarding a nationwide Common Agreement, HCA will determine the need for: 1. a statewide requirement to use a common DSA: (a) for research/QM activities, and (b) at the point of care; OR 2. make available for use (but not require) a common/standard data sharing template for information exchange at the point of care If HCA determines that a statewide requirement to use a common DSA at the point of care is needed, HCA will develop a legislative strategy |  | X |  | Governance | [5 empty] | Data Governance | Legal Office Privacy Office | Participant |  |  | Lead | [5 empty] | Co-Lead | Participant |  | Participant |  |  |  | Co-Lead |  | Participant
Data Governance Strategy | Data Sharing Agreements | 03-018 | If a statewide requirement to use a common/standard DSA is not viable, HCA will encourage the use of standard data share agreement templates between entities engaged in quality measurement activities and health information exchange at the point of care (including exchange of SUD/sensitive information (e.g., Consent Management template)), leveraging the data share agreements established in cooperation between HCA and ACHs |  | X |  | Governance | [5 empty] | HW/Policy | HW/Communications AIM HIT Section | Co-Lead |  |  | Participant | [6 empty] | Co-Lead | co-lead | Lead |  |  |  |  | Participant
Data Governance Strategy | Data Sharing Agreements | 03-019 | HCA will encourage ACHs to partner with local jails and corrections to coordinate release of individuals with community-based health care providers. |  | X |  | Policy | [5 empty] | HIT Section | Data Governance Program |  |  |  | Co-Lead | [6 empty] | Lead |  | Participant |  |  |  |  | Participant | Participant |  |  | Participant | [11 empty] | Participants
Data Analytics | Data Analytics | 04-001 | Business Intelligence Tools: Build out and align internal and external dashboards for all agency Medicaid standard reporting, performance measure reporting, and individual project-driven dashboards. (WHA now has performance measure dashboard, ProvCORE now has one, we are building one in-house by end of MTD, and APCD is going to start up in this domain). RDA is doing measures reporting. HCA is doing measures reporting. We have also mimicked the NY DSRIP dashboard and need to tweak that for HCA. | X | X |  | Analytics | [5 empty] | AIM | EDMA | Lead |  |  | Participant | Co-Lead | [5 empty] | Participant |  | Participant | [5 empty] | Participant | Participant |  |  |  | Participant | [5 empty] | Participant |  |  | Participant
Data Analytics | Data Analytics | 04-002 | Advanced Analytics / Analytic-Ready Data Products - empowering external stakeholders to do their own analytics. | X |  |  | Analytics | [5 empty] | AIM | EDMA | Lead |  |  | Participant | Co-Lead | [5 empty] | Participant |  | Participant | [5 empty] | Participant | Participant |  |  |  | Participant | [5 empty] | Participant |  |  | Participant
Health IT/Health Information Exchange | Health IT/Health Information Exchange | 05-001 | HCA, DOH, DSHS, DOC, Tribal Governments, MCOs, jails, OHP, and ACHs (in collaboration with providers from their communities) will collaborate to address the Tasks below. Tasks will be coordinated with and leverage work related to: Data Governance Strategy and Data Activities. Tasks may involved various Other Participants depending on the focus of the Task. | X | X |  | Governance | [5 empty] | HIT Section | Financial Services ACHs ACH/Providers OHP | Participant |  | Participant |  |  |  |  | Co-Lead |  |  | Lead |  | Participant | Participant |  | Participant |  | Co-Lead | Co-Lead |  | Participant | Participant | Participant | [5 empty] | Co-Lead |  |  | Participant
Health IT/Health Information Exchange | Assessment | 05-002 | Determine the scope and results of recent HIT/HIE assessments of providers within ACHs and whether updated assessments are needed |  | X |  | Technology | [5 empty] | HIT Section | ACH | [10 empty] | Lead | [7 empty] | Co-Lead
Health IT/Health Information Exchange | Assessment | 05-003 | HCA will introduce ACHs, providers, and other stakeholders to the CMS “Health Information Sharing” (HIS) assessment of functions, capabilities, and dimensions as a way to start the conversation as to the need for an assessment of providers' HIS capabilities (e.g., the discussion could focus on prioritized functions/capabilities/dimensions related to Bi-Directional Integration of Physical and Behavioral Health or addressing the Opioid Use public health crisis). |  | X |  | Technology | [5 empty] | HIT Section | ACHs ACH/Providers | Participant |  | Participant |  |  |  |  | Participant |  |  | Lead |  | Participant | Participant |  | Participant |  | Co-Lead | Co-Lead | [14 empty] | Participants
Health IT/Health Information Exchange | Assessment | 05-004 | If updated HIT/health information exchange assessments are needed, HCA will support ACHs in assessing providers’ health information sharing capacity/use of technology solutions to support Demonstration projects HCA’s role include: • securing 10% matching funds (HITECH/MMIS 90/10) (if needed) • Targeting the CMS “HIS” assessment in areas prioritized in collaboration with ACHs and using resources from CMS • supporting the administration of the HIE assessment of targeted providers within ACHs • analyzing assessment results |  | X |  | Finance/Technology | [5 empty] | HIT Section | ACHs ACH/Providers | Participant |  | Participant |  |  |  |  | Participant |  |  | Lead |  | Participant | Participant |  | Participant |  | Co-Lead | Co-Lead | [14 empty] | Participants
Health IT/Health Information Exchange | HIT/HIE Solutions | 05-005 | Collaboratively, HCA, ACHs, and their providers, will identify and consider potential Health IT/health information exchange solutions that could be used and barriers/gaps that limit use of technology solutions in ACH projects including: • technologies needed to transition to VBP (including FIMC) • OHP services including the CDR • EDIE/Pre-manage • Pathways • PDMP • telehealth |  | X |  | Technology | [5 empty] | HIT Section | ACH ACH/Providers |  |  | Participant | [7 empty] | Lead |  | Participant |  |  |  |  | Co-Lead | Co-Lead | [14 empty] | Participants
Health IT/Health Information Exchange | HIE and Indian Health Care Providers | 05-006 | HCA will participate in a “round table” discussions with Tribal Governments to become better informed of issues/concerns with HIT/HIE by Indian Health Care Providers. | X | X |  | Governance | [5 empty] | HIT Section | Tribal Government Leaders | [10 empty] | Lead |  | Participant | [12 empty] | Participant | [5 empty] | Co-Lead
Health IT/Health Information Exchange | HIE and Indian Health Care Providers | 05-007 | HCA will provide a presentation on health information exchange to Tribal Government Leaders (and Indian Health Care Providers) |  | X |  | Technology | [5 empty] | HIT Section | Tribal Government Leaders | [10 empty] | Lead |  | Participant | [12 empty] | Participant | [5 empty] | Co-Lead
Health IT/Health Information Exchange | HIE and Indian Health Care Providers | 05-008 | HCA will consult with Tribal Government leaders to: - understand concerns related to: privacy issues related to HIT/HIE, opt-in/opt-out of HIT activities, patient rights, and the misuse of Tribal patient data; and - seek to identify opportunities for HIE by Indian Health Care Providers in a manner that responds/addresses these concerns. | X | X |  | Governance | [5 empty] | HIT Section | Tribal Government Leaders | [10 empty] | Lead |  | Participant | [12 empty] | Participant | [5 empty] | Co-Lead
Health IT/Health Information Exchange | HIE and Indian Health Care Providers | 05-009 | No later than December 31, 2017, the tribes and IHCPs will submit to the state an IHCP Planning Funds Plan and a Plan for Statewide Improvement of AI/AN Behavioral Health. At the discretion of the tribes and IHCPs, the HIT Section is available for consultation. These Plans will include: - An inventory of the data, health information technology, and population health management systems at tribes, IHS facilities, and UIHPs in Washington State and analogous social service/case management data and information systems at tribes in Washington State; and - Anticipated investments in data, health information technology, and population health management systems at tribes, IHS facilities, and UIHPs and analogous social service/case management data and information systems at tribes to enable tribes, IHS facilities, and UIHPs to implement the strategies and evidence-based and promising practices; | X | X |  | Policy | [5 empty] | Tribal Government Leaders | [11 empty] | Participant | [20 empty] | Lead
Health IT/Health Information Exchange | HIE and Indian Health Care Providers | 05-010 | As provided for in the IHCP Planning Funds Plan and a Plan for Statewide Improvement of AI/AN Behavioral Health, HCA and Tribal Government Leaders will consult and collaborate to identify needed technology solutions and funding sources for the acquisition/use of technology needed for: - health information exchange at the point of care between Indian Health Care Providers (including physical health and behavioral health care providers) and between Indian Health Care Providers and others (e.g., CMT/EDIE, OHP, others); and - population health management activities. |  | X |  | Finance | [5 empty] | Tribal Government Leaders | HIT Section | [10 empty] | Co-lead |  | Participant | [12 empty] | Participant | [5 empty] | Lead
Health IT/Health Information Exchange | Coordination on HIT/HIE tools, funding, and contracting | 05-011 | Based on assessment findings and need for (and barriers/ gaps) for HIE at the point of care, and available HIT/health information exchange tools; HCA and ACHs will collaboratively identify: • shared HIT/health information exchange/care coordination tools • funding for shared HIT/health information exchange tools • shared HIT/health information exchange contracts/contracting language |  | X |  | Policy / Technology / Finance | [5 empty] | HIT Section | ACHs ACH/Providers |  |  | Participant |  |  |  |  | Participant |  |  | Lead |  | Participant |  |  |  |  | Co-Lead | Co-Lead | [14 empty] | Participants
Health IT/Health Information Exchange | Coordination on HIT/HIE tools, funding, and contracting | 05-012 | If needed, HCA will pursue 10% matching funds to support activities (using either MMIS or HITECH 90/10 funding) (e.g., to support: (i) assessment of HIE capacity; (ii) acquisition/use of HIE technologies) | X | X |  | Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead
Health IT/Health Information Exchange | Coordination on HIT/HIE tools, funding, and contracting | 05-013 | HCA will explore the need for and feasibility of using a CRM tool for near-term use by ACHs to monitor provider performance in the MTD. |  | X |  | Technology | [5 empty] | HIT Section | ACHs | Participant | [9 empty] | Lead |  | Participant | [5 empty] | Co-Lead
Health IT/Health Information Exchange | Coordination on HIT/HIE tools, funding, and contracting | 05-014 | If needed, HCA will explore funding options to support CRM tool | X | X |  | Finance | [5 empty] | HIT Section | ACHs | Participant | [9 empty] | Lead |  | Participant | [5 empty] | Co-Lead
Health IT/Health Information Exchange | OHP Services | 05-015 | HCA, in collaboration with OHP, will design and disseminate a quarterly report by provider and MCO that shows progress in who is using the CDR. To the extent feasible, reports will (i) take into account information needs of ACHs and MCOs, and (ii) describe whether/how those information needs are being addressed. |  | X | X | Policy / Technology | [5 empty] | HIT Section | OHP | [10 empty] | Lead |  | Participant |  |  |  |  | Participant | Participant | [8 empty] | Participant | Co-Lead
Health IT/Health Information Exchange | OHP Services | 05-016 | HCA, in collaboration with OHP, will convene a Clinical Group to provide guidance/feedback on the type and format of information (e.g., diagnosis, current med list, interventions, and results) that clinicians would find useful from the CDR. HCA and OHP will consider whether it is possible to distill CCDA/CCDs into a summary report that clinicians would find useful. | X |  |  | Policy | [5 empty] | HIT Section | OHP CQCT |  |  | Co-lead | [7 empty] | Lead | [17 empty] | Co-Lead |  |  |  |  | Participants
Health IT/Health Information Exchange | OHP Services | 05-017 | FHCQ will lead efforts with clinicians, quality of care experts, and others to create "high priority" use cases for the CDR in three arenas: Point of Care, Coordination of Care, and Patient Safety. HCA and OHP participate in FHCQ-led activities. |  | X |  | Policy | [5 empty] | FHQC | Co-lead |  |  | Co-lead | [7 empty] | Participant | [6 empty] | Participant | [6 empty] | Lead |  |  |  | Participant |  |  |  |  | Participants
Health IT/Health Information Exchange | OHP Services | 05-018 | HCA will convene a group of state agency representatives, ACHs, MCOs and providers to prioritize CDR needs to meet the Demonstration and HCAs goals. Group will take into account "ideal state" use cases. |  | X |  | Policy / Technology | [5 empty] | HIT Section | ACHs | Participant |  | Participant |  |  |  |  | Participant |  |  | Lead |  | Participant | Participant |  | Participant |  | Participant | Co-Lead |  | Participant | Participant | [5 empty] | Participant | Participant |  |  |  |  | Participants
Health IT/Health Information Exchange | OHP Services | 05-019 | HCA and OHP will develop a catalog of: - current OHP services - current provider types presently registered - future services/transactions and provider types to be added and timelines for when planned additions will be available. Future services/transactions/providers will take in account "high priority" use case and CDR needs that were prioritized. HCA will disseminate this assessment to state, ACH and provider partners beginning at the end of Q1 and update the assessment every six months thereafter. |  | X |  | Technology | [5 empty] | HIT Section | OHP | [10 empty] | Lead |  | Participant |  |  |  |  | Participant | Participant | [8 empty] | Participant | Co-Lead
Health IT/Health Information Exchange | OHP Services | 05-020 | HCA will work with OHP to: • identify EHR solutions that do not currently support using ProviderOne ID • develop strategy to encourage providers/vendors to include the P1ID for Medicaid patients and/or improve patient matching • implement strategy and track effectiveness | X | X |  | Policy / Technology | [5 empty] | HIT Section | P1OS OHP | [10 empty] | Lead |  | Participant |  |  | Co-Lead |  | Participant | [9 empty] | Participant | Co-Lead
Health IT/Health Information Exchange | OHP Services | 05-021 | HCA will work with OHP to launch the CDR provider portal |  | X |  | Technology | [5 empty] | HIT Section | OHP |  |  | Participant | [7 empty] | Lead | [6 empty] | Participant | [9 empty] | Participant | Co-Lead |  |  |  |  | Participants
Health IT/Health Information Exchange | OHP Services | 05-022 | HCA, in collaboration with Other Participants, will consider the need to provide a means for interested individuals to access their own health information and educational materials that enable the individuals to self-manage their health, their family’s health or others they care for. |  | X |  | Technology | [5 empty] | ETS | P10S |  |  | Participant |  |  |  | Lead |  |  |  | Participant |  | Participant |  |  |  |  | Participant | Participant |  |  |  | Participant |  |  |  |  | Participant | Participant
Health IT/Health Information Exchange | Education / TA | 05-023 | HCA will establish, host, and support a monthly virtual TA meeting venue. HCA will provide /contract for the provision of on-going educational series that will include at a minimum: • recorded monthly webinars • materials (e.g., PPT) that can be disseminated and re-used |  | X |  | Policy | [5 empty] | HW/Communications | HW/Policy HIT Section | Participant | [9 empty] | Co-Lead | Lead | Co-Lead
Health IT/Health Information Exchange | Education / TA | 05-024 | HCA and ACHs, in collaboration with stakeholders, will identify topics for an on-going Educational/TA series on HIT/ health information exchange. Sessions will include basic and more advance topics and may include (to be prioritized by ACHs and HCA): • Behavioral Health billing IT and HIT applications; • Vendor evaluation and selection criteria; • Workflow considerations; • Privacy and security; • Health information sharing • Use of the OHP services including the CDR (e.g., onboarding additional providers to the CDR, and how providers can use the information in the CDR, receive notifications, and identified best practices); and • Use of clinical document architecture in health information exchange activities |  | X |  | Policy | [5 empty] | HW/Policy | ACHs | Participant | [9 empty] | Participant |  | Lead |  |  |  |  | Participant | Co-Lead |  | Participant | Participant | Participant |  |  |  |  | Participant | Participant |  |  | Participant |  | Participants
Health IT/Health Information Exchange | Education / TA | 05-025 | HCA in collaboration with DoH will: • determine the need for TA activities (e.g., focusing on specified information exchange activities with and by behavioral health providers) by QUALIS, and • if needed, determine whether funding sources are available and if available develop plan to deliver TA services that focus on needed HIE |  | X | X | Policy / Finance | [5 empty] | HIT Section | DoH | Participant | [9 empty] | Lead |  | Participant | [7 empty] | Co-Lead
Health IT/Health Information Exchange | Education / TA | 05-026 | HCA will consider the feasibility of and resources needed for implementing alternative technical assistance and training support models (including the current Practice Transformation Hub model services) to assist providers (e.g., physical health, behavioral health, LTC, social service providers) in implementing HIT/HIE solutions to support ACH projects. Such considerations will take into account: the need for such assistance, the results of assessment findings related to HIE/health information sharing, and the need for assistance with the acquisition and use of specific technology solutions and method of assistance (e.g., coaches, webinars, and other activities). |  | x |  | Policy / Technology | [5 empty] | HW/Policy | HIT Section | Participant | [9 empty] | Co-Lead |  | Lead | [5 empty] | Co-lead |  | Participant | Participant | Participant
Health IT/Health Information Exchange | Education / TA | 05-027 | HCA and ACHs will consider the need for and how to educate and advocate with private philanthropic organizations for the creation and identification of opportunities/partnerships to support the integration of physical health, behavioral health, community-based social services to address public and population health care. |  | X |  | Policy | [5 empty] | HW/Policy | ACHs | Participant | [9 empty] | Participant |  | Lead | [5 empty] | Co-lead
Health IT/Health Information Exchange | Education / TA | 05-028 | HCA will perform an annual HIT/HIE roadshow to: • Describe use of/opportunities to use HIT/HIE in ACH projects • evaluate improving increase access to Meaningful Use incentives, • increase ensuring compliance with state and federal requirements, • receive provider input on how to advance standards-based Health IT adoption |  | X | X | Policy / Technology | [5 empty] | HIT Section | HW Communications | Participant |  |  | Participant | Participant | [5 empty] | Lead | Co-Lead | Participant | [20 empty] | Participants
Health IT/Health Information Exchange | Security Practices | 05-029 | HCA will create/contract for the development of a white paper describing best security practices for HIT/HIE. The paper will include consultations with MCO IT Security Officers and Office of Cyber Security The paper will include a description of OHP and MCO security practices and other selected HIE services. |  | X |  | Technology | [5 empty] | ETS | HIT Section |  |  |  |  | Participant |  | Lead |  |  |  | Co-Lead | [16 empty] | Participant | Participant
Health IT/Health Information Exchange | Security Practices | 05-030 | HCA will disseminate the white paper to: ACHs and providers, MCOS, and other stakeholders. |  | X |  | Policy | [5 empty] | HW/Communications | ETS | [6 empty] | co-lead |  |  |  | Participant | Lead
Health IT/Health Information Exchange | Performance Measures HIT/Health Information Exchange | 05-031 | HCA, in consultation with ONC and ACHs, will identify/contract for the identification of performance measures related to the adoption and use of HIT/HIE. |  | X |  | Policy / Technology | [5 empty] | HIT Section | AIM | Co-Lead | [9 empty] | Lead |  | participant | [5 empty] | participant |  |  |  |  | Participant
Health IT/Health Information Exchange | Performance Measures HIT/Health Information Exchange | 05-032 | HCA will convey identified HIT/HIE measures to the MTD independent evaluator. |  |  | X | Policy | [5 empty] | AIM | HW/Policy | Lead | [9 empty] | Lead |  | participant
Health IT/Health Information Exchange | Performance Measures HIT/Health Information Exchange | 05-033 | HCA will disseminate findings, including sharing findings with independent MTD program evaluator |  | X | X | Policy | [5 empty] | AIM | DSHS/RDA | Lead | [9 empty] | Participant | [12 empty] | Co-Lead
Health IT/Health Information Exchange | Incenting HIT/HIE thru VBP | 05-034 | HCA will consider exploring with MCOs: • methods that could be used in managed care arrangements to encourage provider use of HIE technologies for care management/care coordination activities; and • potential payment methodologies that could progressively incent HIE methods (e.g., from paper/fax to electronic to interoperable HIE) | X | X | X | Policy | [5 empty] | HW/Policy | HIT Section | Participant | [9 empty] | co-Lead |  | Lead | [14 empty] | Participant | [5 empty] | Participants
Health IT/Health Information Exchange | Staff HIT/HIE Directory | 05-035 | HCA, in collaboration with ACHs and other stakeholders, will compile, disseminate, and maintain a list and contact information for staff involved in HIT/health information exchange and analytics. The list will be updated quarterly. | X | X |  | Policy | [5 empty] | HW/Policy | ACH | Participant |  |  | Participant | Participant | [5 empty] | Participant |  | Lead |  |  | Participant |  |  | Co-Lead |  | Participant | Participant | Participant |  |  |  |  | Participant |  |  |  | Participant
Health IT/Health Information Exchange |  | 05-036 | HCA will provide ONC with quarterly updates of the most recent executive sponsor dashboard regarding uptake of the CDR. |  | x |  | Policy | [5 empty] | Hit Section
Health IT/Health Information Exchange | Update HIT Documents | 05-037 | Based on the Demonstration's strategic HIT roadmap and this operational plan, HCA will update and align (and as needed going forward) the following documents: | X | X | X | Policy
Health IT/Health Information Exchange | Update HIT Documents | 05-038 | SIM HIT documents -- 2017 | X | X | X | Policy | [5 empty] | AIM | HW/Policy HIT Section | Lead | [9 empty] | Co-Lead |  | Co-lead
Health IT/Health Information Exchange | Update HIT Documents | 05-039 | SIM HIT documents -- 2018 | X | X | X | Policy | [5 empty] | HIT Section |  | Participant | [9 empty] | Lead
Health IT/Health Information Exchange | Update HIT Documents | 05-040 | State HIT Operational Plan | X | X | X | Policy | [5 empty] | HIT Section |  | Participant |  | Participant | Participant | Participant | [5 empty] | Lead |  | Participant |  |  | Participant
Health IT/Health Information Exchange | Update HIT Documents | 05-041 | State Medicaid HIT plan | X | X | X | Policy | [5 empty] | HIT Section |  | Participant |  | Participant | Participant | Participant | [5 empty] | Lead |  | Participant |  |  | Participant
Health IT/Health Information Exchange | Update HIT Documents | 05-042 | HITECH IAPD (as needed) | X | X | X | Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead
Health IT/Health Information Exchange | Update HIT Documents | 05-043 | MMIS IAPD (as needed) | X | X | X | Finance | [5 empty] | P1OS | Financial Services | [7 empty] | Co-Lead |  |  | Participant |  |  |  |  | Lead
Financing | Financing | 06-001 | HCA, in collaboration with Other Participants, will identify potential funding sources that could be used for the 10% state match under HITECH and MMIS funding, including funding sources that could be used to support DOH engagement. | X | X |  | Policy / Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead |  | Participant | [5 empty] | Participant |  | Participant | Participant | Participant |  |  |  |  | Participant | Participant |  |  | Participant |  | Participants
Financing | Financing | 06-002 | HCA will seek guidance from CMS about the feasibility of using identified funding sources for the 10% match | X | X |  | Policy / Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead
Financing | Financing | 06-003 | HCA staff will attend monthly meeting to identify/learn of activities that require funding and consider where there may be opportunities for securing needed funds. | X | X | X | Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead
Financing | Financing | 06-004 | If needed, HCA in consultation with other participants, will develop a legislative strategy to secure the needed 10% match. | X | X | X | Policy / Finance | [5 empty] | HCA Policy | HIT Services Financial Services | [7 empty] | Co-Lead |  |  | Co-Lead |  | Participant |  |  |  | Co-Lead |  | Participant |  | Participant | Participant | Participant |  |  |  |  | Participant | Participant |  |  | Participant |  | Participants
Financing | Financing | 06-005 | HCA and other participants will identify opportunities for shared (braided) Health IT/HIT financial investments. HCA will disseminate information to ACHs, providers, and others as appropriate | X | X | X | Policy / Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead |  | Participant | [5 empty] | Participant |  | Participant | Participant | Participant |  |  |  |  | Participant | Participant |  |  | Participant |  | Participants
Financing | Financing | 06-006 | HCA will (as feasible) support identified funding requests. | X | X |  | Finance | [5 empty] | Financial Services | [8 empty] | Lead |  |  | Participant
Financing | P1 Capabilities | 06-007 | HCA will procure Fraud Abuse Detection System Tools that will be utilized in the Enterprise Data Warehouse database |  | X | X | Policy | [5 empty] | EDMA | MPOI |  |  |  |  | Lead | [5 empty] | Participant |  | Participant |  | co-lead
Master Person Identifier | Master Person Identifier | 07-001 | HCA will discuss options and its authority to convene meetings/discussions to obtain input from external stakeholders on various MPIs used across programs, and PROs/CONs of multiple vs. single MPI | X | X |  | Policy / Governance | [5 empty] | HCA Legal Office | EDMA | Participant |  |  | Participant | Co-Lead |  |  | Participant |  | Lead | Participant |  | Participant |  |  | Participant
Master Person Identifier | Master Person Identifier | 07-002 | Using this legal analysis, HCA may choose (at its sole discretion) to pursue 90/10 MMIS or HITECH funds to contract to implement and use a MPI. | X | X | X | Policy / Finance | [5 empty] | HCA ELT | HCA Legal Office P1OS EDMA Financial Services AIM | Co-Lead |  |  |  | Co-Lead |  |  | Co-Lead | Lead | Co-Lead | Participant |  | Participant |  |  | Co-Lead
Provider Directory | Provider Directory | 08-001 | HCA will determine the feasibility of using 90/10 MMIS or HITECH funding to pursue Provider Directory Tasks below. | X | X | X | Policy / Finance | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead
Provider Directory | Provider Directory | 08-002 | HCA will collaborate with DOH to consider enhancements to the current provider license interface with ProviderOne that would be of value in assessing provider directory options. | X | X | X | Policy | [5 empty] | HIT Section | Financial Services | [7 empty] | Co-Lead |  |  | Lead | [9 empty] | Participant
Provider Directory | Provider Directory | 08-003 | HCA, in collaboration with Other Participants, will identify provider directory information needed to manage provider information for 1-2 uses cases identified in collaboration with ACHs. Consideration will be given to: - information needed (e.g., demographics, physical addresses, credential and specialty information, other information) - business processes to support needed information - Purposes/uses of that information (e.g., HIE, payment, ACH project monitoring) HCA, in collaboration with Other Participants, will identify sources, gaps, and overlaps in needed provider directory information, and consider whether more effective provider directory solutions are needed. HCA will leverage the Manatt Data Strategy Framework. | X | X | X | Policy | [5 empty] | AIM | HIT Section ACH | Lead |  |  | Participant | [6 empty] | Co-Lead |  | Participant |  |  | Participant |  | Participant | co-lead |  | Participant | Participant | Participant | participant |  |  |  | Participant
Data Visualization | Data Visualization | 09-001 | HCA, in collaboration with ACHs and HCA contractor Providence Core, RDA, and DOH will identify and present to leadership approaches for displaying pay for performance measures and providing ACHs with means to explore sub-populations. | X | X | X | Policy | [5 empty] | AIM | EDMA | Co-Lead |  |  |  | Lead | [5 empty] | Participant | Participant | Participant | [5 empty] | Co-Lead |  | Participant | [5 empty] | Participant |  |  | Participant
Data Visualization | Data Visualization | 09-002 | If approved by HCA leadership, HCA in collaboration with DOH and Other Participants will: • determine costs of data visualization techniques (e.g., Tableau); and • identify funding sources. | X | X | X | Finance | [5 empty] | ETS | AIM EDMA | Co-Lead |  |  |  | Lead |  |  | Participant |  |  | Participant | Participant | Participant | [5 empty] | Participant |  | Participant | [5 empty] | Participant |  |  | Participant
Project Evaluation | Project Evaluation | 10-001 | An independent evaluation of the MTD is required under the Demonstration STCs and is governed through contract with CMS. The MTD evaluation includes an assessment of Health IT/ Health Information Exchange activities and will be conducted in accordance with the evaluation protocol submitted and approved by CMS. |  |  | X | Policy | [5 empty] | AIM | HIT Section | Lead | [9 empty] | Co-Lead |  | Participant | [10 empty] | Co-Lead
Project Evaluation | Project Evaluation | 10-002 | HIT-related components of the independent evaluation will be shared with HIT stakeholders/owners. |  |  | X | Policy | [5 empty] | AIM | HW/Communications HIT Section | Lead | [9 empty] | Co-Lead | Co-lead | Participant